## Foglio1
| Sprint 0 | Sprint 1
Issues Opened | 1 | 22
Issues Closed | 0 | 16
| Bug | NFR | Enabler | User Story | Not Labeled
Types of Issues - Opened | 17 | 3 | 4 | 0 | 1
| Bug | NFR | Enabler | User Story | Not Labeled
Types of Issues - Closed | 11 | 1 | 2 | 1 | 1
Work Done | Sprint 0 | Sprint 1
Business Modeling | 0 | 0
Requirements | 7 | 0.25
Analysis and design​ | 7 | 6.25
Implementation | 0 | 19.5
Test | 28 | 8
Deployment | 21 | 0.75
Configuration and change management​ | 0 | 0
Project management​ | 18.5 | 7.25
Environment​ | 0 | 6.5
Total | 81.5 | 48.5